Deakin-DHS (BSWR) Partnership Interim Evaluation Project Timeline

| Week Commencing | Activity |
| --- | --- |
| 15th June 2009 | Draft evaluation tools established |
| 22nd June 2009 | 22nd June: Stage 1 Evaluation Meeting with Public Health Forum Advisory Group Co-Chairs Meeting to discuss evaluation tool demographics 25th June: Stage 1 Evaluation Meetings with Co-Chairs from Teaching and Workforce Development Advisory Group, Research and Evidence-Based Practice Advisory Group, and Health and Wellbeing Advisory Group Note: Evaluation Meetings will involve completion of Mapping exercise as well as formulation of key priorities for each group. |
| 29th June 2009 | Evaluation tool sent for electronic development. |
| 6th July 2009 | Online survey available for use Ethics obtained |
| 13th July 2009 | Survey sent to potential participants – beginning of data collection |
| 20th July 2009 | Data collection |
| 27th July 2009 | Responses received – establish data file |
| 3rd August 2009 | Commence analysis |
| 10th August 2009 | Report preparation |
| 17th August 2009 | Finalise report |

Note: This timeline will depend on how long it takes for ethics to be obtained and for the survey to be produced in an electronic format.