## Instructions
Instructions: Deakin Safety in Design Risk Assessment Template
ID | Title (Project phase?) | Contributing Factors ( Description of the workplace activity ?) | Impact (description of the hazards associated with this activity?) | Highest Impact rating (consequence) description | Likelihood Rating | Inherent rating calculation | Controls (systems, training, documentation, engineering, PPE) | Control rating value | Residual rating value
Insert the activity number | Name the project activity phase | Describe the activitys that will be conducted in some detail | What are they? | Refer to the Deakin risk matrix | Refer to the Deakin risk matrix | Refer to the Deakin risk matrix | See the table below to identify controls Deakin risk matrix rating. | Refer to the Deakin risk matrix | Refer to the Deakin risk matrix
HIERARCHY OF CONTROLS
Having established a level of risk for a hazard, it is then necessary to determine and implement an appropriate control
(or combination of controls if no single measure is sufficient). Below is a guide from most preferred to least preferred control measures.
ELIMINATE THE HAZARD (most preferred) | ELIMINATE - Get rid of the hazard out of the workplace. | » Redesign the work process to remove the hazard
» Redesign of the work process to eliminate exposure
CHANGE THE WAY WORK IS DONE | SUBSTITUTE - Try to replace or change plant, substances or materials to lower the risk from the hazard. | » Consider using air-powered instead of electric powered tools
» Consider using water based paints rather than solvent based ones.
| Try to ISOLATE the hazard | » Insulation (i.e. sound proofing or insulation from the heat)
» Guarding on machines.
| ENGINEERING CONTROL - Design and install equipment to counteract the hazard | » Lifting devices
» Exhaust ventilation system to extract dangerous fumes or dust.
| ADMINISTRATIVE CONTROL Arrange work so people spend less time around the hazard and monitor their understanding of the hazard and the controls | » Health and safety related Training;
» Develop SWMS for staff to follow
» Restricted access to certain work areas, i.e. confined space
» Operator certification for plant
» Job rotation.
PPE (least preferred) | PPE Have people wear protective equipment and clothing while near the hazard | » Is it appropriate for the staff member?
» Does it control the risk for that staff member?
» Does it control the risk?
» Is the staff member informed of any limitations?
» Has the staff member been given instruction and training on the proper use of PPE?

## Design Hazard Categories
Category of hazard | Examples
Siting of building(s) or structure(s) | poor siting or lack of separation
High consequence hazards | storage and handling of dangers goods, work with high energy hazards , biological materials
systems of work | cleaning and maintenance of building that pose a risk; inadequate pedestrian / vehicle separation; restricted access for building and plant maintenance
Environment | Environmental conditiosn that are not part of the speciic system of work, such as inadequate entialation or lighting, welfare facilities
Incident Mitigation | inadequate egress during incident, siting of assembly areas, inadequate emergency services access
Electrical safety
Fire and emergency
movement of people and materials
workign environment
plant
amenities and facilities
earthworks
structural safety
manual tasks
substances
falls prevention
specific risks
Noise
Other

## Risk Register
Risk Register XX/XX/XXXX
Top Ranking Risk and Compliance Items |  |  | Risk Rating Criteria |  |  |  | Mitigation Strategies
ID | Title (Project phase?) | Contributing Factors ( Description of the workplace activity ?) | Impact (description of the hazards associated with this activity?) | Highest Impact rating description | Likelihood Rating | Overall Inherent risk rating ? | Controls (systems, training, documentation, engineering, PPE) | Control rating value | Residual rating value

## lists (hidden)
| likelihood | value | controlrating2 | controls | value |  | category |  |  |  |  | risk | sort order | start | end
6 | Almost certain | 6 | 6 | Excellent | 4 |  | OHS |  |  | 6 | VH | Very High | 6 | 10.01 | 100
4.5 | Likely | 4.5 | 5 | Very Good | 3 |  | Financial |  |  | 5 | H | High | 5 | 7 | 10
3 | Possible | 3 | 4 | Good | 2 |  | Environmental |  |  | 4 | M | Medium | 4 | 5 | 6.9
1.8 | Rare | 1.8 | 3 | Medium | 1 |  | Reputation, Outrage & Media |  |  | 3 | L | Low | 3 | 2 | 4.9
0.5 | Almost impossible | 0.5 | 2 | Poor | 0 |  | University Performance |  |  | 2 | VL | Very Low | 2 | -10 | 1.99
|  |  | 1 | No Controls | -0.5 |  | Regulatory
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
| almost certain |  |  |  |  | likely |  |  |  |  | possible |  |  |  |  | rare |  |  |  |  | almost impossible
| catastrophic | major | substantial | modest | minor | catastrophic | major | substantial | modest | minor | catastrophic | major | substantial | modest | minor | catastrophic | major | substantial | modest | minor | catastrophic | major | substantial | modest | minor
excellent | H | M | M | L | L | M | M | L | L | VL | M | L | L | VL | VL | L | L | VL | VL | VL | L | VL | VL | VL | VL
very good | H | H | M | L | L | H | M | L | L | L | M | L | L | VL | VL | L | L | VL | VL | VL | L | L | VL | VL | VL
good | H | H | H | M | L | H | H | M | L | L | H | M | L | L | VL | M | L | L | VL | VL | L | L | VL | VL | VL
medium | VH | H | H | M | M | H | H | M | M | L | H | M | M | L | L | M | M | L | L | VL | M | L | L | VL | VL
poor | VH | VH | H | H | M | VH | H | H | M | M | H | H | M | L | L | H | M | L | L | L | M | M | L | L | VL
no controls | VH | VH | H | H | H | VH | H | H | M | M | H | H | M | M | L | H | M | M | L | L | H | M | L | L | VL
| VL L L L M M: Impact; M M H H H H: sort order; L L M M H H: value; L L L M M M: 20; L L L M M H: teqsa | live
| L L L M M M: 1; VL L L L M M: Catastrophic; M M H H H H: 1; L L M M H H: 6; L L L M M M: Catastrophic; L L L M M M: 40; L L L M M H: Provider standing | Learning
| H H H VH VH VH: inherent risk; L L L M M M: 2; VL L L L M M: Major; M M H H H H: 2; L L M M H H: 4.5; L L L M M M: Major; L L L M M M: 60; L L L M M H: Financial viability and safeguards | Ideas
| H H H VH VH VH: 1; M H H H VH VH: 2; M M H H H H: 3; L L M M H H: 4; L L L M M H: 5; M H H H VH VH: 6; L L L M M M: 3; VL L L L M M: Substantial; M M H H H H: 3; L L M M H H: 3; L L L M M M: Substantial; L L L M M M: 80; L L L M M H: Corporate and academic governance | Value
| M H H H VH VH: Catastrophic; M M H H H H: Major; L L M M H H: Substantial; L L L M M H: Modest; M H H H VH VH: Minor; L L L M M M: 4; VL L L L M M: Modest; M M H H H H: 4; L L M M H H: 1.8; L L L M M M: Modest; L L L M M M: 100; L L L M M H: Primacy of academic quality and integrity | Experience
| Almost certain | Very High | Very High | High | High | Medium |  |  | 5 | Minor | 5 | 0.5 | Minor | [7 empty] | Management and human resources
| Likely | Very High | High | High | Medium | Medium |  |  | 6 | n/a | 6 | 0 | n/a | [7 empty] | Responsibilities to students
| Possible | High | High | Medium | Low | Low | [14 empty] | Physical and electronic resources and infrastructure
| Rare | High | Medium | Low | Low | Low | [14 empty] | Other
| Almost impossible | Medium | Medium | Low | Low | Very Low
Note on K29: list of names only=impactname

## DLF Risk & Compliance summ (hidden)
Deakin Learning Futures
Top Ranking Risk and Compliance Register 02/04/2012
Top Ranking Risk and Compliance Items | [5 empty] | Risk Rating Criteria | [8 empty] | Mitigation Strategies
ID | Title | Contributing Factors | Implications | TEQSA category | LIVE category | Impact | Impact Ratings | risk rating value | highest impact rating | Highest Impact rating description | Likelihood Rating | likelihood rating value | inherent rating calculation | Overall Inherent rating | Controls | Collective Control Rating | control rating value | residual rating value | Residual Rating | Optimum Rating | Actions | Resource | Target Date | Action Status (% complete)
DLF006 | Move from printed product to digital product (T) (move from analogue to digitial) |  |  | Physical and electronic resources and infrastructure | Experience | Reputation, Outrage & Media | Major | 4.5 | 4.5 | Major | Possible | 3 | 7.5 | High | Staged Approach Plan agreed on by Faculty Management | Medium | 1 | 6.5 | Medium | Low
DLF003 | Loss of reputation resulting from not meeting staff/student expectations/agendas |  |  | Management and human resources | Experience | Reputation, Outrage & Media | Substantial | 3 | 3 | Substantial | Possible | 3 | 6 | Medium | Defining cloud learning as an academic concept (paper) in conjuction with academic community | Good | 2 | 4 | Low | Low
DLF007 | Risk of industrial action |  |  | Management and human resources | Experience | Reputation, Outrage & Media | Substantial | 3 | 3 | Substantial | Possible | 3 | 6 | Medium | Wide consultation | Good | 2 | 4 | Low | Low
DLF005 | Loss of corporate knowledge (T) of staff during/resulting from transition |  |  | Physical and electronic resources and infrastructure | Experience | University Performance | Modest | 1.8 | 1.8 | Modest | Possible | 3 | 4.8 | Low | Gathering of corporate intelligence from all systems (system passwords etc.) | Medium | 1 | 3.8 | Low | Low
DLF001 | Sufficient staff/resources with required skills and focus to meet new strategic directions |  |  | Management and human resources | Experience | Reputation, Outrage & Media | Substantial | 3 | 3 | Substantial | Possible | 3 | 6 | Medium | Transition consultation process | Very Good | 3 | 3 | Low | Low
DLF004 | Risk of low staff morale as a result of transition resulting in lack of cultural shift required to meet new strategic directions |  |  | Management and human resources | Experience | OHS | Modest | 1.8 | 1.8 | Modest | Possible | 3 | 4.8 | Low | Transition consultation process | Very Good | 3 | 1.8 | Very Low | Low | Sign off by Executives
DLF008 | D2L financial sustainability (D2L go bust) (change in focus, structure,direction) Change in focus, structure or direction of D2L adversely impacts on Deakin’s ability to provide flexible education. |  |  | Financial viability and safeguards | Learning | University Performance | Major | 4.5 | 4.5 | Major | Possible | 3 | 7.5 | High | Monitoring | Poor | 0 | 7.5 | High | Low
DLF010 | Student academic results management | D2L interface to complete transfer of student academic grades from Callista has not been implemented | Students academic results in D2L may not be final/up to date | Primacy of academic quality and integrity | Learning | University Performance | Substantial | 3 | 3 | Substantial | Possible | 3 | 6 | Medium | Callista SMS interface has been developed | Medium | 1 | 5 | Medium | Low | CReaTe work stream – CD04 Education where you are implementation | DVC(A) | 2012-12-31 | 20
DLF002 | Cloud Learning (high/main risk) [loss of contol of open resources] |  |  | Physical and electronic resources and infrastructure | Learning | Reputation, Outrage & Media | Substantial | 3 | 3 | Substantial | Possible | 3 | 6 | Medium | Defining cloud learning as an academic concept (paper) in conjuction with academic community | Very Good | 3 | 3 | Low | Medium
DLF009 | Copyright Act (main) (intellectual Property) |  | Breach of licence conditions | Provider standing | Value | Regulatory | Substantial | 3 | 3 | Substantial | Rare | 1.8 | 4.8 | Low | Staff training & communciation | Good | 2 | 2.8 | Low | Low | ITSD Business Analyst to analyse the business processes for 'results management' | ITSD Business Analyst | 2012-06-30 | 20
Note on B13: Snezana Hristovska: risk title to be expanded on and clarified
Note on P13: Snezana Hristovska: controls to be added

## FIOA Risk&Compliance regis sum (hidden)
Internal Audit Unit
Top Ranking Risk and Compliance Register 15/05/2012
Top Ranking Risk and Compliance Items | [5 empty] | Risk Rating Criteria | [8 empty] | Mitigation Strategies
ID | Title | Contributing Factors | Implications | TEQSA category | LIVE category | Impact | Impact Ratings | risk rating value | highest impact rating | Highest Impact rating description | Likelihood Rating | likelihood rating value | inherent rating calculation | Overall Inherent rating | Controls | Collective Control Rating | control rating value | residual rating value | Residual Rating | Optimum Rating | Actions | Resource | Target Date | Action Status (% complete)
IAU001 | [20 empty] | Activities to further promote IAU (e.g. newsletter, brochure, updated website) | Director, IAU | 2012-12-31 | 20
[21 empty] | Coordinate with other assuracne providers to minimise duplication in audits (i.e. VAGO, Risk & Compliance) | Director, IAU | 2012-12-31 | 40
[21 empty] | Audit Manual including methodology being finalised | Director, IAU | 2012-05-31 | 80
IAU002 | [20 empty] | Review success of new processes of mitgating risk | Director, IAU | 2012-12-31 | 20
IAU003 | [20 empty] | Re-tender for 2013 | Director, IAU | 2012-09-30 | 40
IAU004 | [20 empty] | Audit Manual including methodology being finalised | Director, IAU | 2012-05-31 | 80
External Quality review of IAU methodlogy to encourage better practice
IAU005 | [20 empty] | IAU to develop internal Quality Assurance Program (an internal review against standards on more regular basis) | Director, IAU | 2012-12-31 | 20
IAU006 | [20 empty] | Develop and implement local & effective OHS Plan | Director, IAU | 2012-12-31 | 20
|  | Lack of OHS awareness & requirements | [5 empty] | 0 | [6 empty] | Local workplace assessments | [5 empty] | Review travel policies & procedures and implement any changes required | Director, IAU | 2012-12-31 | 20
|  | Uncooperative/aggressive staff during audits (which may cause stress) | [5 empty] | 0 | [6 empty] | The requirement to have two staff present at key meetings | [5 empty] | include in draft audit manual the requirement to have two staff present at key meetings | Director, IAU | 2012-12-31 | 20
|  | Lack of local & effective OHS Plan | [5 empty] | 0 | [6 empty] | Local induction based on Deakin OHS checklist | [5 empty] | Develop and implement manual handling training for IAU staff | Director, IAU | 2012-12-31 | 20
IAU007 | [20 empty] | include backups, security, access in draft audit manual | Director, IAU | 2012-12-31 | 20
|  | Lack of ITSD support for IAU applications including TeamMate | Failure to provide assurance that the University has appropriate governance, risk management and control frameworks in place |  |  | University Performance | Major | 4.5 | [6 empty] | Hardcopy information securely kept in locked cabinets …. | [5 empty] | check with ITSD what the DR provisions are for corporate applications including TeamMate | Director, IAU | 2012-12-31 | 20
|  | Lack of secure storage for hardcopy files | Failure to achieve annual audit plan | [11 empty] | Regular ITSD backups of information
|  | Potential lack of integrity of IAU staff and GT staff | Reputational damage for IAU | [11 empty] | Local copy of TeamMate
|  | failure to adhere to IT security protocols | [12 empty] | GT confidentiality agreement
IAU008 | [7 empty] | 0 | 0 | n/a |  | 0 | 0 | Very Low |  |  | 0 | 0 | Very Low
0
IAU008 | [7 empty] | 0 | 0 | n/a |  | 0 | 0 | Very Low |  |  | 0 | 0 | Very Low
0
0
IAU009 | [7 empty] | 0 | 0 | n/a |  | 0 | 0 | Very Low |  |  | 0 | 0 | Very Low
0
0
IAU010 | [7 empty] | 0 | 0 | n/a |  | 0 | 0 | Very Low |  |  | 0 | 0 | Very Low
0
IAU011 | [7 empty] | 0 | 0 | n/a |  | 0 | 0 | Very Low |  |  | 0 | 0 | Very Low
IAU012 | [7 empty] | 0 | 0 | n/a | Rare | 1.8 | 1.8 | Very Low |  |  | 0 | 1.8 | Very Low
0
0
0
0
IAU013 | [7 empty] | 0 | 0 | n/a | Rare | 1.8 | 1.8 | Very Low |  |  | 0 | 1.8 | Very Low
0
0
0
0
IAU014 | [7 empty] | 0 | 0 | n/a |  | 0 | 0 | Very Low |  |  | 0 | 0 | Very Low
0
0
0
0
IAU015 | [7 empty] | 0 | 0 | n/a |  | 0 | 0 | Very Low |  |  | 0 | 0 | Very Low
0
0
0
0
IAU016 | [7 empty] | 0 | 0 | n/a |  | 0 | 0 | Very Low |  |  | 0 | 0 | Very Low
0
0
0
0